## Valve Master Log
Client: ADNOC OFFSHORE
CONTRACT:- FRAMEWORK AGREEMENT - TECHNICAL SERVICES (CALL-OFF) FOR PROVISION OF VALVES MAINTENANCE SERVICES. REFERENCE #.4700025060 F. Work Order # 4700026048
| Contractor Job Reference |  | ADNOC offshore Reference | [7 empty] | Valve Details | [7 empty] | Loading Note Reference |  |  | Initial Inspection |  | Quotation / Call off order Details | [6 empty] | Job / Delivery Note details |  |  |  |  | Invoice Details
S.No | EMEC JOB ID | ID Number | Work Order | Asset | Location / Platform | Tag Number | Asset/Equipment Number | CID No. | MR Details | LOT No | Valve Type | Size (inch) | Rating | End conn. | Operator Details | Manufacturer | Model / Serial No. | Service requested | Site Dispatch Note | Date of receipt | Delivery CN No. | Initial Inspection Report | Inspection Date | Quotation Ref. | Date | Client Purchase Order | COO Ref. | COO Receipt date | COO Value (AED) | Equipment Final Testing & Acceptance | Job Status | Contractor DN Ref# | Date | Job Officer | Remarks | Invoice Ref. | Invoicing Date | Invoice Amt (AED) | Tax Invoice Status | E-Invoice Ref # | Paid Status
1 | PJ00001119-1 |  | 4700026048 |  | ZCSC | 70-LV-2211 |  |  |  | 1 | Globe Valve |  |  |  | Pneumatic Piston Actuator | Severn Glocon |  | Site Service | [15 empty] | Biduraj Puthan Veettil
Note on AG3456: Divya: Spare Parts deliver to Delivery note number 3566_954
Note on AG3835: Divya: 3566_1020 - 10 Valves we supply to Al Raha 3566_1024 - 98 Valves we supply to Al Raha
Note on D3853: Divya Need send the mail.
Note on A4237: Divya January 2022

## Options
LZ-Lower Zakum | Site Service | Biduraj Puthan Veettil | Bare Stem
US-Umm Shaif | Refurbishment |  | Gear Box
NS-Nasr | OEM Support |  | Hand wheel/Lever
UL-Umm Lulu | Manpower supply |  | Pneumatic Piston Actuator
UZ-Upper Zakum |  |  | Pneumatic Diaphragm Actuator
ST-Satah |  |  | Electrical Actuator (MOV)
UAD-Umm Al Dhalkh |  |  | Hydraulic Actuator
DA-Das |  |  | Electro Hydrolic Actuator
ZR-Zirku
AZ-Arzana
ASSEIFIYA Island (South Island)
ETTOUK Island (North Island)
AL GHALLAN Island (Central Island)
UMM AL ANBAR (West Island)
SARB (S1 & S2 Islands)